## Slide 1: ESTIMATION-1
Estimation is the scientific way of working out the approximate cost of an engineering project before execution of the work.
It is totally different from calculation of the exact cost after completion of the project.
Estimation requires a thorough Knowledge of the construction procedures and cost of materials & labour in addition to the skill , experience, foresight and good judgment.

## Slide 2: ESTIMATE
An estimate of the cost of a construction job is the probable cost of that job as computed from plans and specifications.
For a good estimate the, actual cost of the proposed work after completion should not differ by more then 5 to 10 % from its approximate cost estimate, provided there are no unusual, unforeseen circumstances.

## Slide 3: NEED FOR ESTIMATE
1. It help to work out the approximate cost of the project in order to decide its feasibility with respect to the cost and to ensure the financial resources, it the proposal is approved.
2. Requirements of controlled materials, such as cement and steel can be estimated for making applications to the controlling authorities.
3. It is used for framing the tenders for the works and to check contractor’s work during and after the its execution for the purpose of making payments to the contractor.
4. From quantities of different items of work calculated in detailed estimation, resources are allocated to different activities of the project and ultimately their durations and whole planning and scheduling of the project is carried out.

## Slide 4: SITE CONDITIONS AFFECTING THE OVERALL COST
1 = Each type of work requires a different method of construction. Construction may be of an ordinary house or office and it may also be of a Dam, Tunnel, Multistory building, Airport, Bridge, or a Road, already in operation. Each of these works requires totally different construction techniques, type of machinery, and formwork.
2 = Quality of labour and labour output varies in different localities.
3 = Weather conditions greatly affect the output and, hence, the overall cost.

## Slide 5: SITE CONDITIONS AFFECTING THE OVERALL COST (-ctd-)
4. Ground conditions vary and change the method of construction. For example, excavation may be dry, wet, hard, soft, shallow or deep requiring different efforts.
5. The work may be in open ground such as fields or it may be in congested areas such as near or on the public roads, necessitating extensive watching, lightening, and controlling efforts, etc.

## Slide 6: SITE CONDITIONS AFFECTING THE OVERALL COST (-ctd-)
6. The source of availability of a sufficient supply of materials of good quality is also a factor.
7. The availability of construction machinery also affects the method of construction.
8. Access to the site must be reasonable. If the access is poor, temporary roads may be constructed.

## Slide 7: ESSENTIAL QUALITIES OF A GOOD ESTIMATOR
In preparing an estimate, the Estimator must have good knowledge regarding the important rules of quantity surveying.
He must thoroughly understand the drawings of the structure, for which he is going to prepare an estimate.
He must also be clearly informed about the specifications showing nature and classes of works and the materials to be used because the rates at which various types of works can be executed depend upon its specifications.

## Slide 8: ESSENTIAL QUALITIES OF A GOOD ESTIMATOR (-ctd-)
A good estimator of construction costs should possess the following capabilities, also:-
1 = A knowledge of the details of construction work.
2 = Experience in construction work.
3 = Having information regarding the materials required, machinery needed, overhead problems, and costs of all kinds.
4 = Good judgment with regard to different localities, different jobs and different workmen.
5 = Selection of a good method for preparing an estimate.
6 = Ability to be careful, thorough, hard working and accurate.
7 = Ability to collect, classify and evaluate data relating to estimation.
8 = Ability to visualize all the steps during the process of construction.

## Slide 9: ESSENTIAL QUALITIES OF A GOOD ESTIMATOR (-ctd-)
Before preparing the estimate, the estimator should visit the site and make a study of conditions, there. For example, if the construction of a large building is planned, the estimator or his representative should visit the site and:
Note the location of the proposed building.
Get all data available regarding the soil.
Make a sketch of the site showing all important details.
Obtain information concerning light, power, and water.
Secure information concerning banking facilities.
Note conditions of streets leading to railway yards and to material dealers, and
Investigate general efficiency of local workman.

## Slide 10: TYPES OF ESTIMATES
There are two main types of estimates:-
1 = Rough cost estimate.
2 = Detailed estimate.
Depending upon the purpose of estimate, some types of detailed estimate are as follows:-
Contractor's estimate
Engineer's estimate
Progress estimate

## Slide 11: I = Rough cost estimate
Estimation of cost before construction from plans or architectural drawings of the project scheme, when even detailed or structural design has not been carried out, is called Rough cost estimate.
These estimates are used for obtaining Administrative Approval from the concerning Authorities.
Sometimes, on the basis of rough cost estimates, a proposal may be dropped altogether.

## Slide 12: Rough cost estimate (-ctd-)
Unit cost is worked out for projects similar to the project under consideration carried out recently in nearly the same site conditions.
Unit cost means cost of execution of a unit quantity of the work.

## Slide 13: Rough cost estimate (-ctd-)
To find rough cost of any project, this worked average unit cost is multiplied with total quantity of the present work in the same units.
For example, in case of a building, plinth area (sq. ft.) of the proposed building is worked out, which is then multiplied by the cost per unit area (Rs. /ft2) of similar building actually constructed in the near past in nearly the same site conditions, to find out the rough cost estimate of the building.
This cost is sometimes adjusted by the average percentage rise in the cost of materials and wages.

## Slide 14: Rough cost estimate
The rough cost estimate may be prepared on the following basis for different types of projects:
1. Cost per square foot of covered area (plinth area) is the most commonly adopted criterion for preparing rough cost estimate for most of the residential buildings.
2. For public buildings, cost. Per person (cost per capita) is used. For example,
Students hostel———————-—cost per student
Hospitals————————————Cost per bed
Hotel—————————————Cost per Guest

## Slide 15: Rough cost estimate (-ctd-)
Cost per cubic foot is particularly suitable for commercial offices, shopping centers, and factory buildings, etc.
For water tank/reservoir, cost may be worked out on the basis of capacity in gallons of water stored.
For roads and railways, cost may be found out per mile/kilometer of length.
For streets, cost may be per hundred feet/meters of length.
7. In case of bridges, cost per foot/meter of clear span may be calculated.

## Slide 16: EXAMPLE
Calculate the total rough cost estimate and cost per Flat for a multi-storey (4-storeyed) block consisting of 40 residential flats. Other details are given in the table:

## Slide 17
Sr. No | PORTION | AREA (sq. ft) | UNIT COST (Rs./sq.ft.) |  |  | 
 |  |  | Building Works | Sanitory Works | Electric Services | Sui Gas Services
1 | Main Flat Area (i) Ground Floor (ii) Ist Floor (iii) 2nd Floor (iv) 3rd Floor | 20030 20030 20030 20030 | 1800 1500 1650 1800 | 130 130 130 130 | 100 100 100 100 | 60 60 60 60
2 | Park Area at G. Floor | 75,800 | 800 | -------- | 40 | -------
3 | Circulation Area in all 4 floors | 1936 | 1050 | -------- | 70 | -------
4 | Covered Shopping Area at G. Floor | 920 | 950 | -------- | 70 | -------
5 | Attached Servant Quarters | 2112 | 1150 | 55 | 70 | 40

## Slide 18: Add the following costs as Lump Sum :
1- Road and Walkways = 15,00,000/-
2- Land Scapping = 12,00,000/-
3- External Sewerage = 7,00,000/-
4- External Water Supply, Overhead and Underground Water Tanks with pumping machinery for each set of Flats = 19,00,000/-
5- External Electricity = 3,00,000/-
6- Boundary Wall = 6,00,000/-
7- Miscellaneous unforeseen items
    = 8,00,000/-
8- Add 6 % development charges.
9- Add 3 % consultancy charges

## Slide 19: EXAMPLE 2
Prepare a Rough-cost Estimate of a residential building project with a total plinth area of all building of 1500 sq.m. given that:
linth Area Rate = Rs: 950.00 / sq. ft.
Extra for special architectural treatment = 1.5 % of the buiding cost.
Extra for water supply and sanitary installations = 5 % of the building cost.
Extra for internal installations = 14 % of the buiding cost
Extra for Electric & Sui gas services = 16 % of buiding cost
Contigencies 3 % overall
Supervision charges = 8 % overall
Design charges = 2 % overall

## Slide 20: EXAMPLE 3
Prepare a Rough-cost Estimate based on unit costs of per unit plinth area basis of a four storeyed office building having a carpet area of 2000 sq.m. for obtaining the administrative approval of the Government. It may be assumed that 30 % of the built up area will be taken by the corridors, verandas, lavatories, staircase, etc. and 10 % of built up area will be occupied by walls. The following data is given:
Plinth Area Rate = Rs: 1100.00 / sq. ft.
Extra for special architectural treatment = 0.5 % of the buiding cost.
Extra for water supply and sanitary installations = 6 % of the building cost.

## Slide 21: Example 3
Extra for internal installations = 14 % of the buiding cost
Extra for electric services = 12.5 % of buiding cost
Extra for sui gas services = 6 % of buiding cost
Extra due to deep foundations at site = 1.0 % of buiding cost
Contigencies = 2.5 % overall
Supervision charges = 8 % overall
Design charges = 2.5 % overall

## Slide 22: Example 4
Prepare a Rough-cost Estimate for obtaining the administrative approval of the Government for a hospital project to serve both indoor and outdoor patiesnts in an important rural area. The hospital will consist of the following:
Main administrative office with dispensing operations, etc.
Two general wards, each of 20 general beds.
Superintendent Doctor’s Residence.
Two Assistant Doctor’s Residences.
Eight single Nurses Quarters.
Four Compounder’s Quarters.
Twelve lower staff’s Quarters.

## Slide 23: DETAILED ESTIMATE
Detailed estimates are prepared by carefully and separately calculating in detail the costs of various items of the work that constitute the whole project from the detailed working drawings after the design has been finalized.
The mistakes, if any, in the rough cost estimate are eliminated in the detailed estimate.
Detailed estimates are submitted to the competent authorities for obtaining technical sanction.

## Slide 24: DETAILED ESTIMATE
The whole project is sub-divided into different items of work or activities. The quantity for each item is then calculated separately from the drawings as accurately as possible. The procedure is known as "taking out of quantities".
The quantities for each item may be estimated and shown in the pattern which is called "Bill of quantities."
The unit, in which each item of the wok is to be calculated, should be according to the prevailing practice as followed in various departments of the country.

## Slide 25
BILL OF QUANTITIES
Sr. No | Description of item | No | Measurements |  |  | Quantity | Total Quantity | Remarks
 |  |  | Length | Breadth | Height |  |  | 

## Slide 26
PRICED BILL OF QUANTITIES
Sr. No. | Description of Item | Unit | Quantity | Rate | Cost | Remarks

## Slide 27: DETAILED ESTIMATE
Each item of the work is then multiplied by its estimated current rate calculated by a fixed procedure to find out cost of the item.
At the end, a total of all items of the work are made to get the total estimated cost.
The rates are usually as per Schedule of Rates for the locality plus a premium to allow for rise in labor and material rates over and above the schedule of rates.
A percentage, usually 5% is also provided on the total estimated cost for the work to allow for the possible contingencies due to unforeseen items or expenditure or other causes, besides 2% establishment charges.

## Slide 28: DETAILED ESTIMATE
Besides drawings and details of measurements and calculation of quantities (Bill of Quantities), the following documents are also usually submitted with the detailed estimate for obtaining Technical Sanction:
A report explaining History, necessity, scope and main features of the project, its design, and estimate, etc.
2. Specifications lying down the nature and class of work and material to be used in various parts of the work.
3. The abstract of cost (priced Bill of Quantities) showing the total quantities under each sub-head, rate per unit of measurement, and cost.
4. Calculation sheets showing calculations for important parts of the structure. In fact, in estimating the art and skill lies only in the computation of details without any omissions, of all parts of the building or work.

## Slide 29: CLASSIFICATION DEPENDING UPON PURPOSE OF DETAILED ESTIMATE
1- CONTRACTOR ESTIMATE It is made by the contractor for determining the price or prices to be bid. It is usually a carefully prepared detailed estimate.
2- ENGINEER’S ESTIMATE
This type of estimate is made by the Engineer (Consultant) usually for the purposes of financing the work and for checking bids and running bills submitted by contractors.

## Slide 30: 3- PROGRESS ESTIMATES
These are made by the Engineer at regular intervals for the completed parts of the project during the progress of the work for determining the amounts of partial payments to be made to the contractor.
On large contracts, such estimates are commonly made each month and, hence, are frequently called monthly estimates.

## Slide 31: UNFORESEEN ITEMS IN DETAILED ESTIMATE
While preparing a detailed estimate, one had to be very careful to see that all items of the work are incorporated.
It is likely that a few Items, though unimportant in nature, might have been overlooked and which may result in raising the estimate of the project.
There may be also certain unforeseen circumstances affecting the project.
Hence, a certain allowance usually 5 to 10% of the total cost, is made in the estimation which will take care of all these items that are unforeseen or are overlooked and are known as "Contingencies".

## Slide 32: METHODS OF DETAILED ESTIMATE
The dimensions, length, breadth and height or depth are to be taken out from the working drawings (plan, elevation and section).
Junctions of walls, corners and the meeting points of walls require special attention.
For symmetrical footings, which is the usual case, earthwork in excavation in foundations, foundation concrete, brickwork in foundation and plinth, and brickwork in superstructure may be estimated by either of the two methods:
(1) SEPARATE OR INDIVIDUAL WALL METHOD
(2) CENTER LINE METHOD

## Slide 33: SEPARATE OR INDIVIDUAL WALLS METHOD
The walls running in one direction are termed as "long walls” and the walls running in the transverse direction, as "Short waLls", without keeping in mind which wall is lesser in length and which wall is greater in length.
Lengths of long walls are measured or found "Out-to out" and those of short walls as "In-to-in".
Different quantities are calculated by multiplying the length by the breadth and the height of the wall.
The same rule applies to the excavation in foundation, to concrete bed in foundation, D.P.C., masonry in foundation and super structure etc.

## Slide 34: SEPARATE OR INDIVIDUAL WALLS METHOD
For symmetrical footing on either side, the center line remains same for super structure, foundation and plinth. So, the simple method is to find out the centre-to-centre lengths of long walls and short walls from the plan.
Long wall length out-to-out
= Center to center length + half breadth on one Side + half breadth on other side.
= Center to center length + one breadth
Short wall length in-to-in = Center to Center length - one breadth.

## Slide 35: SEPARATE OR INDIVIDUAL WALLS METHOD
This method can also be worked out in a quicker way., as follows:
For long walls
First of all, find the length of the foundation trench of the long wall “out-to-out” in the same manner as explained above.
The length of the foundation concrete is the same.
For the length of the first footing or first step of the brick wall, subtract two offsets (2x6"=12") in foundation concrete from the length of the trench or concrete.
For the second footing subtract from the length of the 1st footing two offsets (2x2.25"= 4.5"), for 3rd footing subtract from the length of the 2nd footing 2 offsets (4.5") and in this way deal with the long walls up to the super-structure.
For short walls
Follow he same method but instead of subtracting add two offsets to get the corresponding lengths in-to-in.

## Slide 36
Foundation
Trench
1 Breadth
2
1 Breadth
2

## Slide 37: CENTRE LINE METHOD
In this method, total length of centre lines of walls, long and short, has to be found out.
Find the total length of centre lines of walls of same type, having same type of foundations and footings and then find the quantities by multiplying the total centre length by the respective breadth and the height.
In this method, the length will remain the same for excavation in foundations, for concrete in foundations, for all footings, and for superstructure (with slight difference when there are cross walls or number of junctions).
This method is quicker but requires special attention and considerations at the junctions, meeting points of partition or cross walls.

## Slide 38: CENTRE LINE METHOD
For rectangular, circular polygonal (hexagonal, octagonal etc) buildings having no inter or cross walls, this method is quite simple.
For buildings having cross or partition walls, for every junction, half breadth of the respective item or footing is to be deducted from the total centre length.
Thus in the case of a building with one partition wall or cross wall having two junctions, deduct one breadth of the respective item of work from the total centre length.

## Slide 40: CENTRE LINE METHOD
For buildings having different types of walls, each set of walls shall have to be dealt separately.
Find the total centre length of all walls of one type and proceed in the same manner as described above. Similarly find the total centre length of walls of second type and deal this separately, and so on.
Suppose the outer walls (main walls) are of A type and inner cross walls are of B type.
Then all A type walls shall be taken jointly first, and then all B type walls shall be taken together separately.
In such cases, no deduction of any kind need be made for A type walls, but when B type walls are taken, for each junction deduction of half breadth of A type walls (main Walls) shall have to be made from the total centre length of B type walls.

## Slide 41: CENTRE LINE METHOD
At corners of the building where two walls are meeting, no subtraction or addition is required.
In the figure, the double cross-hatched areas marked P,Q,R, & S come twice, while blank areas, A,B,C, & D do not come at all, but these portions being equal in magnitude, we get the correct quantity.